## Payment schedule by deliverable
Budget Template 1. Payment Schedule by Task and Deliverable
Task | Subtask | Deliverable | Due | Cost |  |  | Total Cost for Task
|  |  |  | Base Period | Option Period I | Option Period II
1. Project Kickoff (February 2017) |  | Materials for summer orientation, training of coaches, and feedback and coaching program | Materials within six working days of the subcontract award date Meeting within eight working days of the subcontract award
2. Site Recruitment Assistance (February 2017 through May 2017) |  | Program summary | Within five working days of the subcontract award date
|  | Frequently asked questions document | Within five working days of the subcontract award date
|  | Review of select recruitment materials | Ongoing through May 2017
|  | Participation in recruitment calls (up to 15) | Ongoing through May 2017
3. Finalize feedback and coaching program materials, as needed (February 2017 through April 2017) |  | Revised program materials | 2017-04-03
4. Hire, train, and assign coaches | 4.1 Hire, train, and assign coaches to novice teachers (February 2017 through June 2017) | Revised hiring, training, and staffing plan for coaches of novice teachers | 2017-05-31
| 4.2 Hire, train, and assign coaches to early career teachers (February 2018 through June 2018) | Revised hiring, training, and staffing plan for coaches of early career teachers | 2018-03-01
5. Coordinate transfer of videos from camera provider | 5.1 Coordinate transfer of videos for novice teachers (April 2017 through October 2017) | Test transfer of videos from IRIS Connect to the coaching provider | 2017-04-28
|  | Transfer of videos from IRIS Connect to the provider | Within one week of recording each video
| 5.2 Coordinate transfer of videos for novice teachers (November 2017 through April 2018) | Transfer of videos from IRIS Connect to the provider | Within one week of recording each video
| 5.3 Coordinate transfer of videos for early career teachers (July 2018 through October 2018) | Transfer of videos from IRIS Connect to the provider | Within one week of recording each video
| 5.4. Coordinate transfer of videos for early career teachers (November 2018 through April 2019) | Transfer of videos from IRIS Connect to the provider | Within one week of recording each video
6. Finalize summer orientation and feedback and coaching program plans | 6.1. Finalize summer orientation and feedback and coaching program plans for novice teachers (February 2017 through May 2017) | Final plan for summer orientations and feedback and coaching program for novice teachers | 2017-05-31
|  | Final summer orientation agenda | 2017-05-31
| 6.2. Finalize summer orientation and feedback and coaching program plans for early career teachers (February 2018 through May 2018) | Final plan for summer orientations and feedback and coaching program for early career teachers | 2018-04-02
|  | Final summer orientation agenda | 2018-04-02
7. Implement feedback and coaching program for novice teachers | 7.1. Summer orientation and fall implementation of full intervention for novice teachers (July 2017 through October 2017) | Conduct summer orientation session in each district | TBD
|  | Conduct feedback and coaching cycles | TBD
|  | Provide weekly status update on coaching cycles | Weekly during implementation
|  | Completed weekly coaching logs | Weekly during implementation
| 7.2. Winter/spring implementation of full intervention for novice teachers (November 2017 through April 2018) | Conduct feedback and coaching cycles | TBD
|  | Provide weekly status update on coaching cycles | Weekly during implementation
|  | Completed weekly coaching logs | Weekly during implementation
| 7.3. Summer orientation and fall implementation of less intensive intervention for novice teachers (July 2017 through October 2017) | Conduct summer orientation session in each district | TBD
|  | Conduct feedback cycles | TBD
|  | Provide weekly status update on feedback cycles | Weekly during implementation
|  | Completed weekly coaching logs | Weekly during implementation
| 7.4. Winter/spring implementation of less intensive intervention for novice teachers (November 2017 through April 2018) | Conduct feedback cycles | TBD
|  | Provide weekly status update on feedback cycles | Weekly during implementation
|  | Completed weekly coaching logs | Weekly during implementation
| 7.5. Review and respond to implementation issues and successes (April 2018 through May 2018) | Meeting attendance and summary of any agreed-upon revisions | Five working days after meeting
8. Implement feedback and coaching program for early career teachers | 8.1. Summer orientation and fall implementation of full intervention (July 2018 through October 2018) | Conduct summer orientation session in each district | TBD
|  | Conduct feedback and coaching cycles | TBD
|  | Provide weekly status update on coaching cycles | Weekly during implementation
|  | Completed weekly coaching logs | Weekly during implementation
| 8.2. Winter/spring implementation of full intervention (November 2018 through April 2019) | Conduct feedback and coaching cycles | TBD
|  | Provide weekly status update on coaching cycles | Weekly during implementation
|  | Completed weekly coaching logs | Weekly during implementation
9. Project management | 9.1. Project management (February 2017 through October 2017) | Monthly progress reports | Within 10 working days of the first of each month
|  | Weekly meetings during implementation period | Weekly
| 9.2. Project management (November 2017 through June 2018) | Monthly progress reports | Within 10 working days of the first of each month
|  | Weekly meetings during implementation period | Weekly
| 9.3. Project management (July 2018 through October 2018) | Monthly progress reports | Within 10 working days of the first of each month
|  | Weekly meetings during implementation period | Weekly
| 9.4. Project management (November 2018 through June 2019) | Monthly progress reports | Within 10 working days of the first of each month
|  | Weekly meetings during implementation period | Weekly
Total Base Period (sum of all costs in column E)
Total Option Period I (sum of all costs in column F)
Total Option Period II (sum of all costs in column G)
Total (all budget periods) (sum of all costs in column H)

## Itemized budget with staffing
Budget Template 2. Itemized Budget with Staffing
|  | 1 Project Kickoff (February 2017) |  | Task 1 Total Project Kickoff |  | 2 Site Recruitment Assistance (February 2017 through May 2017) |  | Task 2 Total Site Recruitment Assistance |  | 3. Finalize Feedback and Coaching Program Materials (as needed) (February 2017 through April 2017) |  | Task 3 Total Finalize Feedback and Coaching Program Materials (as needed) |  | 4.1 Hire, Train, and Assign Coaches to Novice Teachers (February 2017 through June 2017) |  | 4.2 Hire, Train, and Assign Coaches to Early Career Teachers (February 2018 through June 2018) |  | Task 4 Total Hire, Train, and Assign Coaches |  | 5.1 Coordinate Transfer of Videos for Novice Teachers (April 2017 through October 2017) |  | 5.2 Coordinate Transfer of Videos for Novice Teachers (November 2017 through April 2018) |  | 5.3 Coordinate Transfer of Videos for Early Career Teachers (July 2018 through October 2018) |  | 5.4 Coordinate Transfer of Videos for Early Career Teachers (November 2018 through April 2019) |  | Task 5 Total Coordinate Transfer of Videos from Camera Provider |  | 6.1 Finalize Summer Orientation and Feedback and Coaching Program Plans for Novice Teachers (February 2017 through May 2017) |  | 6.2 Finalize Summer Orientation and Feedback and Coaching Program Plans for Early Career Teachers (February 2018 through May 2018) |  | Task 6 Total Finalize Summer Orientation and Feedback and Coaching Program Plans |  | 7.1 Summer Orientation and Fall Implementation of Full Intervention for Novice Teachers (July 2017 through October 2017) |  | 7.2 Winter/spring Implementation of Full Intervention for Novice Teachers (November 2017 through April 2018) |  | 7.3 Summer Session and Fall Implementation of Less Intensive Intervention for Novice Teachers (July 2017 through October 2017) |  | 7.4 Winter/spring Implenettion of Less Intensive Intervention for Novice Teachers (November 2017 through April 2018) |  | 7.5 Review and Respond to Implementation Issues and Successes |  | Task 7 Total Implement Feedback and Coaching Program for Novice Teachers |  | 8.1 Summer Session and Fall Implementation of Full Intervention (July 2018 through October 2018) |  | 8.2 Winter/spring Implementation of Full Intervention (November 2018 through April 2019) |  | Task 8 Total Implement Feedback and Coaching Program for Early Career Teachers |  | 9.1 Project Management (February 2017 through October 2017) |  | 9.2 Project Management (November 2017 through June 2018) |  | 9.3 Project Management (July 2018 through October 2018) |  | 9.4 Project Management (November 2018 through June 2019) |  | Task 9 Total Project Management |  | Total
Budget period |  | Base |  |  |  | Base |  |  |  | Base |  |  |  | Base |  | Option Period I |  |  |  | Base |  | Option Period I |  | Option Period I |  | Option Period II |  |  |  | Base |  | Option Period I |  |  |  | Base |  | Option Period I |  | Base |  | Option Period I |  | Option Period I |  |  |  | Option Period I |  | Option Period II |  |  |  | Base |  | Option Period I |  | Option Period I |  | Option Period II
|  | Hours | Cost | Hours | Cost | Hours | Cost | Hours | Cost | Hours | Cost | Hours | Cost | Hours | Cost | Hours | Cost | Hours | Cost | Hours | Cost | Hours | Cost | Hours | Cost | Hours | Cost | Hours | Cost | Hours | Cost | Hours | Cost | Hours | Cost | Hours | Cost | Hours | Cost | Hours | Cost | Hours | Cost | Hours | Cost | Hours | Cost | Hours | Cost | Hours | Cost | Hours | Cost | Hours | Cost | Hours | Cost | Hours | Cost | Hours | Cost | Hours | Cost | Hours | Cost
Name | Title
Name | Title
Name | Title
Name | Title
Name | Title
Name | Title
Name | Title
Name | Title
Name | Title
Name | Title
Total Labor
Fringe
ODCs
Printing and reproduction
Materials and supplies
Consultants/Outside Services
Postage
Communications
Travel
Other (specify)
Other Indirect/Administrative Fee
Fee (if applicable)
Total Costs